# AGREEMENT

This agreement (the “Agreement”) is effective for the period of April 20, 2018 until the completion of the project on July 20, 2018.

BETWEEN:

COMPANY; Education 20/20 Inc. located in Charlottetown, PEI,

(the “Company”)

AND:

MRSB Consulting Services Inc, 139 Queen Street, Charlottetown, PE< C1A 8C3

(the “Consultant”)

WHEREAS:

The “Company” accepts the “Consultant’s” consulting services, for their mutual benefit and pursuant to a working relationship which has been established for the purposes of Undertaking an Assessment of Continuing Education and Workforce Development Needs in the Souris Area of PEI at cost not to exceed $32,051;00 including HST.

- THE PARTIES AGREE AS FOLLOWS:

The Consultants “Proposal to Undertake Assessment of Continuing Education and Workforce Development Needs in the Souris Area” dated February 13, 2018 and undated addendum constitutes part of this agreement. The Consultant shall provide to the Company the services described in Appendix A attached hereto (the ”Services”).

2	CONFIDENTIALITIES

Consultant, its directors, officers, employees, advisors, agents and assigns shall:

  - keep confidential all information relating to the Company that is disclosed, communicated, or otherwise provided to the Consultant by the Company, including any and all documents, reports, correspondence, data, studies, or other information prepared by, on behalf of, or for the benefit of the Consultant or for the purposes of or related to this Agreement (the “Confidential Information”);

  - use the Confidential Information solely to perform its obligations under the Agreement and not directly or indirectly for any other purpose;

  - not disclose, reproduce, copy, or otherwise duplicate the Confidential information except as with the express written consent of the Company or as required by law.

3	NO WAIVERS

No provision of this Agreement will be deemed waived or any breach excused, unless such waiver or consent is granted prior to the breach and in writing.

4	ASSIGNMENTS

Neither party may assign all or part of this Agreement without the prior written consent of the other party.

5.	ENTIRE AGREEMENT

This Agreement contains the entire agreement and understanding of the parties with respect to its subject matter and supersedes all prior proposals, negotiations, agreements, understandings, representations and warranties of any form or nature.

6		GOVERNING LAW AND JURISDICTION

This Agreement will be governed by and construed under the laws of Prince Edward Island and the applicable laws of Canada.

7		INFORMATION

The Consultant will not use the Information for any purpose other than to assist in the developmental process and to evaluate the information for the purpose of the project’.

8		IDEMNIFY

The Consultant shall indemnify and hold harmless the Company. Its agents, representatives and employees from and against all claims, demands, losses, costs, damages, actions, suits and proceedings of every nature and kind whatsoever arising out of or resulting from the performance of work.

9		PAYMENTS

Upon receipt of invoice, the Contractor will be paid for the Services in accordance with and as described in Appendix “B” attached hereto.

- 10		OTHER REQUIREMENTS AND CONDITIONS

- The Consultant shall provide reasonable access for representatives of the Company and representatives of SKILLSPEI, the Funder, to inspect and assess progress and results of the project.

- The survey incentive of $250 is not being funded as part of this agreement.

11	RECEIVING INFORMATION

The representatives of the respective organizations hereby acknowledge that they have read and will comply with the terms of this Agreement and agree to ensure that all Consultant’s employees are informed of the obligations under this Agreement.

Company’s Representative			Consultant’s Representative

Receiving INFORMATION				Receiving INFORMATION

from Consultant					from Company

Signature: _____________________	Signature: ____________________

Name:    Donald Glendenning  				Name:

Title:       President				Title:

Date: 	                        	  ,  2018		Date:	                                , 2018

IN WITNESS WHEREOF the parties have executed this Agreement:

# Education 20/20 Inc. 				MRSB 	Consulting Services Inc,

by its duly authorized officer:				by its duly authorized officer:

Signature:							Signature:

Name:	Donald Glendenning						Name:

Title: President							Title:

Date:	                                , 2018		Date:	                              , 2018

Signature _______________________

Name:	     William Whelan

Title;  Vice President

Date:

M-6

APPENDIX A

SERVICES

- The Consultant shall perform the following Services:

- Prepare background document review and secondary data research to identify current or previous services, reports, or evaluations related to continuing education in the Souris area.

- Conduct an environmental scan (primary/secondary research) of innovative approaches to continuing education in rural areas.

- Identify the target audience, including students and workers in the Souris Area;

- Develop an interview guide.

- Collect data with government representatives via telephone interview (e.g., Skills PEI, Department of Workforce and Advanced Learning)

- Analyze interview data

- Present interview data to the Company

- Design a survey to identify the continuing education needs and workforce development needed among adults in the Souris area as well as the available supports and recommended strategy to address gaps and better meet needs;

- Ensure the survey questionnaire is a minimum of 6 pages as per Skills PEI requirements;

- ensure a minimum sample size of 500 completed surveys from the Souris population;

- Conduct descriptive and inferential data analysis.

- Present the outcome of the survey analysis to the Company the data collected;

- Prepare a strategy, including recommendations for the delivery of services (degree of match and gap analysis), outline potential sources of support for proposed services, and outline a strategy for future monitoring of delivery and outcomes of continuing education (metrics related to community, workforce, and economic development.

- Prepare a detailed report of the findings from the study and a presentation to the Company;

- Facilitate the dissemination of the findings from the study with key stakeholders and community members at during the month of July.

- Recommend a strategy to address and enhance accessibility /delivery of needed services.

- The Consultant agrees to complete the project no later than July 20, 2018.

- The Consultant shall be responsible for the completion of the work and deliverables as described above and shall report to: Dr. Don Glendenning.

APPENDIX B

FEES AND PAYMENT

Budget

Professional Fees			$25,000

HST on Professional Fees		$  2,250

Surveys				$  4,801

Total						$32,051.00

Fees and Payment Schedule:

- The Consultant shall provide the Services for a total fee of $32,051 including applicable taxes to be paid upon receipt of invoice and provided that the project is completed to the satisfaction of the Company.

- The Company will pay 30% upon commencement of the project; 30% upon presentation of preliminary findings from interviews and surveys; and 20% upon submission of draft report and 20% upon submission of final report and public presentation.

HST Information:

- To receive payment, a valid business invoice must be issued to the Company containing a HST registration number or information indicating that the business is not required to be registered for HST purposes.

- Any HST charged will be calculated at the PEI HST rate.