# MATH FOR EVERY-DAY LIVING

1-8-math

| Organization |  |
| --- | --- |
| Name | Education 20/20 Inc |
| Mission / Mandate | A quality education for every Canadian |
| Address | 101 Kent Street, Box 624, Charlottetown, PE C1A 1M0 |
| Contact Name | Don Glendenning |
| Contact Info | pei@education2020.ca (902) 892-5859 (Res) URL pei@education2020.ca |
| Donation Information |  |
| Name | Math skills map |
| Target Group | Islanders seeking to improve their mathematics skills, and the people who help and hire them |
| Challenge/ Issue | This proposal arises out of a series of discussion and information gathering with providers and users of mathematics in PEI.. Mathematics is a key skill for all citizens; difference in levels can be attributed to the number of skills demonstrated, the level reached on each skill, the degree and extent of clustering by learners and the relevance of benchmarks. Each provider on PEI, it seems, has its approach to determining skills to be taught, how to measure and how to report. This proposal is focused on identifying and describing math skills needed by citizens in their everyday life including entry level employment. Curriculum development normally starts with an analysis of the subject under study; Education 20/20 believes that, instead, it should start by asking Islanders about the math they use, need and want in every-day life. This is the model used during the early years of Holland College. and involves working with practitioners through an analysis process. Education 20/20 proposes to convene a local group of citizens, including employers, and to undertake such an analysis. With analysis in hand, we will strike two profiles, one for citizens and another for Islanders seeking to enter lemployment. Part of the process of striking profiles includes consultation with employers, |
| Description | We propose to develop a map of math skills used by Islanders in everyday life. - Convene a small group, perhaps 10 people, such as parents, teachers, employers. Community workers, etc. - With the aid of a trained facilitator and, using a recognized analysis process, identify a map of math skills used in everyday life. - Strike a profile of skills deemed appropriate for n Island citizen in the 21st century. - Strike a profile of skills needed for work entry level |
| Outcomes | The project will deliver a basic map or master list of competencies used by typical Islanders in their day to day operation. Copies will be made available at cost to any Islander wanting to improve his or her math skills; such a list will also be useful to teachers, tutors, counsellors, employers, credentialing and certification bodies and others. It is also a communication tool between and among various providers ad users of math services. |
| Facilitation | We did not find a facilitator in PEI experienced in leading a user-based skills analysis, however, we’ve found the someone in BC willing to work with us on the project. (see costing below). With map in hand, however, the follow-up work can be done locally although not included as part of this proposal |
| Workplan | Once funding is secured, Education 20/20 will: - Establish s project committee - Let contract with facilitator - Set date for analysis session - Secure facilities: Meeting room secured (a large blank wall suitable for posting committee e suggestions and conclusions) - Arrange support – tables. chairs, space for observers, card writer, refreshments, meals, committee member costs, etc. - Develop map - Identify profiles - Format and print maps |
| Budget and Financial Statement | - Contract with facilitator - $8.900 - Profile development (2) 1,000 - Facilities 350 - Sustenance: 900 - Projector 250 - M&S: cards, paper, pens; formatting 250 - Printing of charts 400 - Project administration 1,250 - Honourarium to committee members2,500 Total $14,250 |
|  | NOTES: - While Education 10/20 is focused on curriculum, the map itself is useful for many other purposes including assessment, qualifications, employment a nd educational counselling, reporting progress, ets. - Project will commence as soon as project approved and analyst is available - Project will be completed within 30 days from commencement Math 2019-1 |