Math Map

Project notes

ProPlan-5D

- End of project deliverables: A math map (estimated 125 competencies) showing the competencies needed by citizens to flourish in the 21st century, a holistic style rating scale appropriate for rating identified competencies, and a profile or profiles of competencies that meet the need for entry level employment.

- Map:

- Facilitators: 2 people for two days and a panel of 10-12 people $7,500

- Room:, ; checked at Royalty Centre ad    Inn on the Hill; good walls (painted cement block?),   U-shaped table  for panel, table and chairs for facilitators $350

- Refreshments morning and afternoon, lunch  15 peoplex2 days x $20=$600; coffee and refreshments $250

- Equipment: Computer projector 1 day $200, screen or good wall, place cards, flip chart, markers,

- Identify and invite panel, all admin support, small ‘thank you” to unpaid panel members  $500

- Deliverables: Bernadette: Electronic copy ready for printing plus misc notes

- Deliverables  wanted by 20/20: electronic copy ready for printing including our logo; something like”with 20/20 logo, original cards from wall,

- 5 Observer seats

- Training for an Islander?

- Rating Scale

- Local committee

- 2 half-days

- Local facilitator $1,500

- Refreshments $100

- Employment entry profile

- 6 local employers for a half-day

- Local facilitator $750

- Refreshments  $50

- Elaborations

- Estimated 125 competencies @ $15.00 = $1,800, electronic and one hard copy of each; will seek out eachers or teachers in raining

- Learning Guide

- Paper  and electronic copy of each

- 125 competencies @40.00 = $5,000

- Will seek out teachers or teachers in training

- Administration

- I think that we need a project administrator to manage the project and report to  our committee. Project administrator? $

- Distribution: Generally available to any interested party; one; free? How many copies: print your own. Who should get complimentary set? $

- Propose to prepare in English but, seek funds to translate into French if there is an interest